## User Stories
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
Complaint System | Farmer | 1.1 Add a new complaint | I can submit a new complaint | Farmer should be logged in. | The field must not be null. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (6 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (3 hrs) | 2 | 13 hours | 2020-08-10 | 2020-08-12 |  | Harshit Joshi |  | Given the farmer has to submit the complaint,when the minimum amd maximum condition of word limit is satisfied,the complaint can be posted. | Given the farmer has to submit the complaint,when the minimum amd maximum condition of word limit is not satisfied,the complaint can not be posted.
| Admin | 1.2 View a complaint | I can view all the complaints | Admin should be logged in. | Complaint ID must be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (6 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (3 hrs) | 2 | 13 hours | 2020-08-13 | 2020-08-17 |  |  |  | Given the admin has to view the complaint,the admin will search the appropriate complaint ID to view the complaint status. | Given the admin has to view the complaint,the admin will search the appropriate complaint ID to view the complaint status. If the complaint ID is not in database,it will display no Complaints Found
| Admin | 1.3 Update a complaint Status | I can update complaint status to read/solved. | Admin should be logged in. | Complaint ID must be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (6 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (3 hrs) | 2 | 13 hours | 2020-08-18 | 2020-08-20 |  |  |  | Given the admin has to update the complaint,the admin will select the appropriate option to read/solved to update the complaint status. | Given the admin has to update the complaint,if the admin will not select the appropriate option it will ask to select the appropriate option.
Crops Service | Farmer | 1.1 Add a new crop | I can sell that crop | Farmer should be logged in. | Farmer ID must be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (6 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (3 hrs) | 2 | 13 hours | 2020-08-10 | 2020-08-14 |  | Gaurav Mohanty |  | Given the farmer has to give crop name and price with quantity so that the sell request can be posted | Given the farmer has to submit the sell request, failing in giving any of the required information, it will not be posted
| Supplier | 1.3 Update the crops | I can update crop requests to accept/reject. | Supplier should be logged in. | Supplier ID must be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (6 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (3 hrs) | 2 | 13 hours | 2020-08-15 | 2020-08-20 |  |  |  | Given the supplier needs to update the crop request added by farmer to accept or reject. | Given the supplier needs to update the crop request added by farmer to accept or reject,if not selected appropriate options the status can not be updated.
Farming Tips Service | Farmer | 1.1 View the farming tips | I can view the farming tips | Farmer should be logged in. | The field must not be null. | 1.Wireframe creation (1 hr) 2. Writing test cases (1 hr) 3. UI design (7 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (4 hrs) | 2 | 13 hours | 2020-08-10 | 2020-08-12 |  | Reema Kumari |  | Given the farmer can view their farming tips . | Given the farmer can view their farming tips, its not satisfied when tips is not posted by admin .
| Admin | 1.2 Add a farming tips | I can add all the farming tips | Admin should be logged in. | Farmer ID must be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (6 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (3 hrs) | 2 | 13 hours | 2020-08-13 | 2020-08-16 |  |  |  | Given the admin has to right to add the farming tips for farmers. | Given the admin has to right to add the farming tips for farmers,not satisfied if its not posted by admin.
| Admin | 1.3 Update a farming tips. | I can update the farming tips | Admin should be logged in. | Farmer ID must be present in the database. | 1.Wireframe creation (1 hr) 2. Writing test cases (1 hr) 3. UI design (7 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (4 hrs) | 2 | 13 hours | 2020-08-17 | 2020-08-19 |  |  |  | Given the admin has to right to update the farming tips . | Given the admin has to right to update the farming tips, not satisfied if its not updated by admin.
| Admin | 1.3 Delete a farming tips. | I can delete the farming tips | Admin should be logged in. | Farmer ID must be present in the database. | 1.Wireframe creation (1 hr) 2. Writing test cases (1 hr) 3. UI design (7 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (4 hrs) | 2 | 13 hours | 2020-08-20 | 2020-08-22 |  |  |  | Given the admin has to right to delete the farming tips . | Given the admin has to right to delete the farming tips,not satisfied if its not deleted by admin.
Authentication system | Admin | 1.1 Login | I can view all the complaints and can add tips | Admin should be logged in. | Should add valid details. | 1.Wireframe creation (1 hr) 2. Writing test cases (1 hr) 3. UI design (7 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (4 hrs) | 2 | 13 hours | 2020-08-10 | 2020-08-12 |  | Manoj Kumar M |  | Given the admin has to login with proper ID and password, If the credentials are valid then he will be logged in. | Given the admin has to login with proper ID and password, If the credentials are not valid then a error message will print and admin will not able to login.
| Supplier | 1.2 Login | I can add, update or delete the requirements. | Supplier should be logged in. | Supplier details must be present in the database. | 1.Wireframe creation (1 hr) 2. Writing test cases (1 hr) 3. UI design (7 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (4 hrs) | 2 | 13 hours | 2020-08-13 | 2020-08-17 |  |  |  | Given the supplier has to login with ID and password, If the entered credentials are valid he will be successfully logged in. | Given the supplier has to login with ID and password, If the entered credentials are not valid then a error message will be displayed and he will not be able to login.
| Farmer | 1.2 Login | I can response to the requirements. | Farmer should be logged in. | Farmer details must be present in the database | 1.Wireframe creation (1 hr) 2. Writing test cases (1 hr) 3. UI design (7 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (4 hrs) | 2 | 13 hours | 2020-08-18 | 2020-08-20 |  |  |  | Given the farmar has to login with ID and password, If the entered credentials are valid then he will be successfully logged in. | Given the farmar has to login with ID and password, If the entered credentials are not valid then a error message will be displayed as "Invalid credentials" and he will not be able to login.
Advertisment Service | Farmer | 1.1 View the advertisment | he can accept reject the crop on the basis of availability | Farmer should be logged in. | Farmer ID must be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (6 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (3 hrs) | 2 | 13 hours | 2020-08-10 | 2020-08-14 |  | Yash Raj |  | Given the farmer has to view advertisments from database, when the appropriate data exists in the database, then farmer will be able to view advertisments. | Given the farmer has to view advertisments from database, when the appropriate data does not exists in the database, then farmer will not be able to view advertisments.
| Supplier | 1.2 Add a new Advertisment | A sms will go to farmer for the advertisment | Fields should be of specified format | No field should be null | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (6 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (2 hr) 6.Controller layer (3 hrs) | 2 | 13 hours | 2020-08-15 | 2020-08-20 |  |  |  | Given the supplier needs to give all the detail in correct format to post the advertisment. | If the crops required by the farmer is not present in the sell information from farmer, supplier will not be able to buy.

## Yash Raj TDD Test Case
|  | TDD Test | Test Data | Cases
Test Case | Test Case Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Enter the crop id in id field. | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | crop id : 0 | post successfully | id should be greater than 0 | fail
2 | Enter the crop id in id field. | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | crop id : -2 | post successfully | id should be greater than 0 | fail
3 | Enter the crop id in id field. | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | crop id : 1 | post successfully | post successfully | pass
4 | Enter the crop id in id field. | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | crop id : 101 | post successfully | id should be less than 100 | fail
5 | Enter the crop name in namefield. | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | crop name: corn | post successfully | post successfully | pass
6 | Enter the crop name in namefield. | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | crop name: co | post successfully | crop name has atleast 3 character | pass
7 | Enter the crop name in namefield. | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | crop name: | post successfully | crop name can not be blank | fail
8 | Enter the quantity field | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | quantity: 2 | post successfully | post successfully | pass
9 | Enter the quantity field | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | quantity: 0 | post successfully | quantity can not be zero | fail
10 | Enter the quantity field | 1) Go to site http://localhost:8083/postadvertisement 2) click on post advertisement 3) Enter details. 4) click on post button. | quantity: null | post successfully | quantity can cnot be null | fail

## Harshit Joshi TDD Test Cases
TDD Test Cases
Test Case | Test Case Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Enter the complaint in the complaint message box field. | "1. Go to site http://localhost:8083/submitcomplaint 2. Enter complaint. 3.Click on the button 'send'. | Complaint ID : 12345 ,Complaint Message : good fertilizers required | Complaint send successfully. | Complaint send successfully. | Pass
2 | Enter the complaint in the complaint message box field. | "1. Go to site http://localhost:8083/submitcomplaint 2. Enter complaint. 3.Click on the button 'send'. | Complaint ID : 12345 ,Complaint Message : good | Complaint send successfully. | Complaint message must be between 20 - 250 characters. | Fail
3 | Enter the complaint in the complaint message box field. | "1. Go to site http://localhost:8083/submitcomplaint 2. Enter complaint. 3.Click on the button 'send'. | Complaint ID : 12345 ,Complaint Message : With the introduction of agriculture mankind entered upon a long period of meanness, misery, and madness, from which they are only now being freed by the beneficent operation of the machine. | Complaint send successfully. | Complaint message must be between 20 - 250 characters. | Fail

## Gaurav Mohanty TDD Test Cases
|  | TDD Test | Test Data | Cases
Test Case | Test Case Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Farmer adds a new crop which he wants to sell. | 1. Go to site 2. Login with id and password 3. Enter the crop details, price and quantity | Crop name Farmer ID Price Quantity | Crop added Succesfully | Crop added ssuccessfully | Pass
2 | Farmer wants to sell the crop without mentioning quantity | 1. Go to site 2. Login with id and password | Crop name Supplier ID Price | Crop update successful | Crop add Failed | Fail
3 | Supplier wants to buy the crops being sold by the farmer | 1. Go to site 2. Login with id and password 3. Enter the crop details, price and quantity | Crop name Supplier ID Price Quantity | Crop Buy Succesful | Crop Buy Succesful | Pass
4 | Supplier wants buy the crop without mentioning the quantity | 1. Go to site 2. Login with id and password 3. Enter the crop details, price and quantity | Crop name Supplier ID Price | Crop Buy Succesful | Crop Buy Failed | Fail

## Reema Kumari TDD Test Cases
|  | TDD Test | Test Data | Cases
Test Case | Test Case Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Add the farming tips in the tips message box field for Admin. | "1. Go to site http://localhost:9090/addTips 2. Enter tips. 3.Click on the button 'send'. | Tips ID :1001,Tips Message : fertilizers | Tips send successfully. | Tips send successfully. | Pass
2 | Update the farming tips in the tips message box field for Admin. | "1. Go to site http://localhost:9090/updateTips 2. Enter tips. 3.Click on the button 'update' using tipsId. | Tips ID :1001,Tips Message : use fertilizers | Tips update successfully. | Tips message must be between 20 - 250 characters. | Fail
3 | Delete the farming tips for Admin. | "1. Go to site http://localhost:9090/deleteTips 2.Click on the delete button using tipsId. | Tips ID :1001,Tips Message : fertilizers | Tips delete successfully. | Not required while deleting | Fail
4 | View the farming tips for Farmers. | "1. Go to site http://localhost:9090/viewtTps 2. Click on the view button''. | Tips ID :1001,Tips Message : Farmers must be use Fertilizers so that these substances contain plant nutrients such as nitrogen,phosphorus and potassium. | Tips view successfully. | Not required while viewing. | Pass

## Manoj Kumar TDD Test Cases
TDD Test Cases
Test Case | TestCase Scenario | TestSteps | Test Data | Expected results | Acutal results | Pass/Fail
1 | Check Admin Login with valid data | 1.Go to site http://localhost:8081/AdminLogin 2.Enter UserId 3.Enter Password 4.Click Login | Id=admin password=pass1234 | Admin should be able to Login to the application
2 | Check Admin Login with invalid data | 1.Go to site http://localhost:8081/AdminLogin 2.Enter UserId 3.Enter Password 4.Click Login | Id=admin password=pass1111 | Admin should not be able to Login to the application
3 | Check Supplier Login with valid data | 1.Go to site http://localhost:8081/SupplierLogin 2.Enter UserId 3.Enter Password 4.Click Login | SID=viru password=12345 | Supplier should able to login to the application
4 | Check Supplier Login with invalid data | 1.Go to site http://localhost:8081/SupplierLogin 2.Enter UserId 3.Enter Password 4.Click Login | SID=viru password=13425 | Supplier should not be able to login to the application
5 | Check Farmar Login with valid data | 1.Go to site http://localhost:8081/FarmarLogin 2.Enter UserId 3.Enter Password 4.Click Login | FID=John password=noodles | Farmar should be able to login into the application
6 | Check Farmar Login with invalid data | 1.Go to site http://localhost:8081/FarmarLogin 2.Enter UserId 3.Enter Password 4.Click Login | FID=John password=noodle | Farmar should not be able to login to the application